## Sheet1
Website Project Master Checklist
Status key:
| ⬜ Not started | 🔄 In progress · | ✅ Completed | ⚠️ Needs review | ❌ Blocked
⬜ Not started
0. Project Setup & Client Requirements | ⬜ Not started
⬜ Not started
Project information | ⬜ Not started
⬜ Not started
⬜ Confirm client/company name | ⬜ Not started
⬜ Not started
⬜ Confirm project/contact person | ⬜ Not started
⬜ Not started
⬜ Confirm website purpose | ⬜ Not started
⬜ Not started
⬜ Confirm target audience | ⬜ Not started
⬜ Not started
⬜ Confirm required pages | ⬜ Not started
⬜ Not started
⬜ Confirm deadline | ⬜ Not started
⬜ Not started
⬜ Confirm budget/payment terms | ⬜ Not started
⬜ Not started
⬜ Confirm who will provide content | ⬜ Not started
⬜ Not started
⬜ Confirm who will provide domain | ⬜ Not started
⬜ Not started
⬜ Confirm who will provide hosting | ⬜ Not started
⬜ Not started
⬜ Confirm who owns the final website/assets | ⬜ Not started
⬜ Not started
⬜ Create project folder | ⬜ Not started
⬜ Not started
⬜ Create Git repository | ⬜ Not started
⬜ Not started
⬜ Create project task checklist | ⬜ Not started
⬜ Not started
Requirements | ⬜ Not started
⬜ Not started
⬜ Collect required pages | ⬜ Not started
⬜ Not started
⬜ Collect required sections for each page | ⬜ Not started
⬜ Not started
⬜ Identify required forms | ⬜ Not started
⬜ Not started
⬜ Identify contact/WhatsApp functionality | ⬜ Not started
⬜ Not started
⬜ Identify social-media links | ⬜ Not started
⬜ Not started
⬜ Identify map/location requirements | ⬜ Not started
⬜ Not started
⬜ Identify SEO requirements | ⬜ Not started
⬜ Not started
⬜ Identify analytics requirements | ⬜ Not started
⬜ Not started
⬜ Identify any third-party integrations | ⬜ Not started
⬜ Not started
⬜ Identify whether CMS/admin editing is required | ⬜ Not started
⬜ Not started
⬜ Identify whether backend is required | ⬜ Not started
⬜ Not started
⬜ Identify whether database is required | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
1. Asset Collection | ⬜ Not started
⬜ Not started
Brand assets | ⬜ Not started
⬜ Not started
⬜ Get official logo | ⬜ Not started
⬜ Not started
⬜ Get logo in highest available resolution | ⬜ Not started
⬜ Not started
⬜ Get transparent PNG/SVG logo | ⬜ Not started
⬜ Not started
⬜ Get favicon/logo mark | ⬜ Not started
⬜ Not started
⬜ Get brand colors | ⬜ Not started
⬜ Not started
⬜ Get brand fonts if available | ⬜ Not started
⬜ Not started
⬜ Get brand guidelines if available | ⬜ Not started
⬜ Not started
Images | ⬜ Not started
⬜ Not started
⬜ Collect hero images | ⬜ Not started
⬜ Not started
⬜ Collect company/about images | ⬜ Not started
⬜ Not started
⬜ Collect service images | ⬜ Not started
⬜ Not started
⬜ Collect project/portfolio images | ⬜ Not started
⬜ Not started
⬜ Collect team photos | ⬜ Not started
⬜ Not started
⬜ Collect testimonial photos | ⬜ Not started
⬜ Not started
⬜ Collect background images | ⬜ Not started
⬜ Not started
⬜ Collect certificates/awards | ⬜ Not started
⬜ Not started
⬜ Collect other visual assets | ⬜ Not started
⬜ Not started
Image processing | ⬜ Not started
⬜ Not started
⬜ Remove unnecessary duplicate images | ⬜ Not started
⬜ Not started
⬜ Rename assets logically | ⬜ Not started
⬜ Not started
⬜ Check image quality | ⬜ Not started
⬜ Not started
⬜ Resize oversized images | ⬜ Not started
⬜ Not started
⬜ Compress images | ⬜ Not started
⬜ Not started
⬜ Convert suitable images to WebP/AVIF | ⬜ Not started
⬜ Not started
⬜ Check transparency where required | ⬜ Not started
⬜ Not started
⬜ Verify image orientation | ⬜ Not started
⬜ Not started
⬜ Verify image cropping | ⬜ Not started
⬜ Not started
⬜ Create asset folder structure | ⬜ Not started
⬜ Not started
Example: | ⬜ Not started
⬜ Not started
assets/ | ⬜ Not started
├── logo/ | ⬜ Not started
├── icons/ | ⬜ Not started
├── hero/ | ⬜ Not started
├── about/ | ⬜ Not started
├── services/ | ⬜ Not started
├── projects/ | ⬜ Not started
├── team/ | ⬜ Not started
├── testimonials/ | ⬜ Not started
└── misc/ | ⬜ Not started
⬜ Not started
Asset verification | ⬜ Not started
⬜ Not started
⬜ Every required image is available | ⬜ Not started
⬜ Not started
⬜ No important image is missing | ⬜ Not started
⬜ Not started
⬜ No low-resolution image is being used unnecessarily | ⬜ Not started
⬜ Not started
⬜ Logo is correct | ⬜ Not started
⬜ Not started
⬜ Colors are correct | ⬜ Not started
⬜ Not started
⬜ No copyrighted/unauthorized asset is being used | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
2. Content Collection | ⬜ Not started
⬜ Not started
Text | ⬜ Not started
⬜ Not started
⬜ Company name | ⬜ Not started
⬜ Not started
⬜ Tagline | ⬜ Not started
⬜ Not started
⬜ Hero heading | ⬜ Not started
⬜ Not started
⬜ Hero description | ⬜ Not started
⬜ Not started
⬜ About content | ⬜ Not started
⬜ Not started
⬜ Services content | ⬜ Not started
⬜ Not started
⬜ Project descriptions | ⬜ Not started
⬜ Not started
⬜ Team information | ⬜ Not started
⬜ Not started
⬜ Testimonials | ⬜ Not started
⬜ Not started
⬜ FAQ | ⬜ Not started
⬜ Not started
⬜ CTA text | ⬜ Not started
⬜ Not started
⬜ Footer content | ⬜ Not started
⬜ Not started
Contact information | ⬜ Not started
⬜ Not started
⬜ Phone number | ⬜ Not started
⬜ Not started
⬜ WhatsApp number | ⬜ Not started
⬜ Not started
⬜ Email | ⬜ Not started
⬜ Not started
⬜ Address | ⬜ Not started
⬜ Not started
⬜ Google Maps location | ⬜ Not started
⬜ Not started
⬜ Business hours | ⬜ Not started
⬜ Not started
⬜ Social media accounts | ⬜ Not started
⬜ Not started
Legal | ⬜ Not started
⬜ Not started
⬜ Privacy policy | ⬜ Not started
⬜ Not started
⬜ Terms if required | ⬜ Not started
⬜ Not started
⬜ Cookie notice if required | ⬜ Not started
⬜ Not started
⬜ Copyright information | ⬜ Not started
⬜ Not started
Content verification | ⬜ Not started
⬜ Not started
⬜ Spelling checked | ⬜ Not started
⬜ Not started
⬜ Grammar checked | ⬜ Not started
⬜ Not started
⬜ Phone numbers verified | ⬜ Not started
⬜ Not started
⬜ Email verified | ⬜ Not started
⬜ Not started
⬜ Address verified | ⬜ Not started
⬜ Not started
⬜ Links verified | ⬜ Not started
⬜ Not started
⬜ Client approved content | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
3. Design & Reference | ⬜ Not started
⬜ Not started
Design collection | ⬜ Not started
⬜ Not started
⬜ Get website reference/design | ⬜ Not started
⬜ Not started
⬜ Collect desktop reference | ⬜ Not started
⬜ Not started
⬜ Collect mobile reference | ⬜ Not started
⬜ Not started
⬜ Collect individual section references if available | ⬜ Not started
⬜ Not started
⬜ Identify inspiration websites | ⬜ Not started
⬜ Not started
⬜ Identify elements that MUST remain unchanged | ⬜ Not started
⬜ Not started
Design analysis | ⬜ Not started
⬜ Not started
⬜ Analyze header | ⬜ Not started
⬜ Not started
⬜ Analyze navigation | ⬜ Not started
⬜ Not started
⬜ Analyze hero | ⬜ Not started
⬜ Not started
⬜ Analyze section structure | ⬜ Not started
⬜ Not started
⬜ Analyze cards | ⬜ Not started
⬜ Not started
⬜ Analyze buttons | ⬜ Not started
⬜ Not started
⬜ Analyze typography | ⬜ Not started
⬜ Not started
⬜ Analyze colors | ⬜ Not started
⬜ Not started
⬜ Analyze spacing | ⬜ Not started
⬜ Not started
⬜ Analyze images | ⬜ Not started
⬜ Not started
⬜ Analyze footer | ⬜ Not started
⬜ Not started
⬜ Analyze mobile layout | ⬜ Not started
⬜ Not started
⬜ Identify animations/interactions | ⬜ Not started
⬜ Not started
AI prompt preparation | ⬜ Not started
⬜ Not started
⬜ Upload design to Claude | ⬜ Not started
⬜ Not started
⬜ Run visual-design analysis | ⬜ Not started
⬜ Not started
⬜ Generate Copilot prompt | ⬜ Not started
⬜ Not started
⬜ Review generated prompt | ⬜ Not started
⬜ Not started
⬜ Correct inaccurate assumptions | ⬜ Not started
⬜ Not started
⬜ Add project-specific requirements | ⬜ Not started
⬜ Not started
⬜ Finalize Copilot prompt | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
4. Website Architecture | ⬜ Not started
⬜ Not started
Before coding: | ⬜ Not started
⬜ Not started
⬜ Decide tech stack | ⬜ Not started
⬜ Not started
⬜ Decide frontend framework | ⬜ Not started
⬜ Not started
⬜ Decide CSS approach | ⬜ Not started
⬜ Not started
⬜ Decide whether backend is required | ⬜ Not started
⬜ Not started
⬜ Decide whether database is required | ⬜ Not started
⬜ Not started
⬜ Decide hosting platform | ⬜ Not started
⬜ Not started
⬜ Decide domain | ⬜ Not started
⬜ Not started
⬜ Decide image storage | ⬜ Not started
⬜ Not started
⬜ Decide form/email solution | ⬜ Not started
⬜ Not started
⬜ Decide analytics solution | ⬜ Not started
⬜ Not started
Example | ⬜ Not started
⬜ Not started
Frontend | ⬜ Not started
React + Vite | ⬜ Not started
⬜ Not started
Styling | ⬜ Not started
CSS / Tailwind | ⬜ Not started
⬜ Not started
Backend | ⬜ Not started
None | ⬜ Not started
⬜ Not started
Forms | ⬜ Not started
External form/email service | ⬜ Not started
⬜ Not started
Hosting | ⬜ Not started
Static hosting | ⬜ Not started
⬜ Not started
Domain | ⬜ Not started
Client's existing domain | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
5. Initial Project Setup | ⬜ Not started
⬜ Not started
⬜ Create project | ⬜ Not started
⬜ Not started
⬜ Initialize Git | ⬜ Not started
⬜ Not started
⬜ Create GitHub repository | ⬜ Not started
⬜ Not started
⬜ Add .gitignore | ⬜ Not started
⬜ Not started
⬜ Install required dependencies | ⬜ Not started
⬜ Not started
⬜ Confirm development server works | ⬜ Not started
⬜ Not started
⬜ Confirm production build works | ⬜ Not started
⬜ Not started
⬜ Set project structure | ⬜ Not started
⬜ Not started
⬜ Add assets | ⬜ Not started
⬜ Not started
⬜ Add fonts | ⬜ Not started
⬜ Not started
⬜ Create basic global styles | ⬜ Not started
⬜ Not started
Project structure | ⬜ Not started
⬜ Not started
Example: | ⬜ Not started
⬜ Not started
src/ | ⬜ Not started
├── components/ | ⬜ Not started
├── pages/ | ⬜ Not started
├── assets/ | ⬜ Not started
├── styles/ | ⬜ Not started
├── data/ | ⬜ Not started
└── utils/ | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
6. Build — Global Design System | ⬜ Not started
⬜ Not started
⬜ Set primary color | ⬜ Not started
⬜ Not started
⬜ Set secondary color | ⬜ Not started
⬜ Not started
⬜ Set accent color | ⬜ Not started
⬜ Not started
⬜ Set background colors | ⬜ Not started
⬜ Not started
⬜ Set text colors | ⬜ Not started
⬜ Not started
⬜ Set font family | ⬜ Not started
⬜ Not started
⬜ Set heading hierarchy | ⬜ Not started
⬜ Not started
⬜ Set button styles | ⬜ Not started
⬜ Not started
⬜ Set border radius | ⬜ Not started
⬜ Not started
⬜ Set shadows | ⬜ Not started
⬜ Not started
⬜ Set container width | ⬜ Not started
⬜ Not started
⬜ Set spacing system | ⬜ Not started
⬜ Not started
⬜ Set responsive breakpoints | ⬜ Not started
⬜ Not started
⬜ Not started
⬜ Not started
7. Build — Header | ⬜ Not started
⬜ Not started
⬜ Logo | ⬜ Not started
⬜ Not started
⬜ Navigation | ⬜ Not started
⬜ Not started
⬜ CTA | ⬜ Not started
⬜ Not started
⬜ Contact information | ⬜ Not started
⬜ Not started
⬜ Mobile menu | ⬜ Not started
⬜ Not started
⬜ Header spacing | ⬜ Not started
⬜ Not started
⬜ Header height
⬜ Header background
⬜ Header border/shadow
⬜ Sticky behavior if required
⬜ Desktop testing
⬜ Mobile testing
8. Build — Homepage
Hero
⬜ Hero background/image
⬜ Overlay
⬜ Heading
⬜ Description
⬜ CTA
⬜ Secondary CTA
⬜ Image positioning
⬜ Responsive layout
Section 1
⬜ Layout
⬜ Heading
⬜ Content
⬜ Images
⬜ Buttons
⬜ Responsive layout
Section 2
⬜ Layout
⬜ Content
⬜ Cards
⬜ Images
⬜ Buttons
Section 3
⬜ Layout
⬜ Content
⬜ Cards/images
⬜ Responsive behavior
Repeat for every section.
9. Build — Individual Pages
For every page:
Page
⬜ Desktop layout
⬜ Mobile layout
⬜ Header
⬜ Hero/page title
⬜ Main sections
⬜ Images
⬜ CTA
⬜ Footer
⬜ Navigation links
⬜ SEO metadata
⬜ Responsive behavior
Example:
Pages
⬜ Home
⬜ About
⬜ Services
⬜ Projects
⬜ Project Details
⬜ Contact
⬜ Privacy Policy
10. Functionality
⬜ Navigation works
⬜ Mobile menu works
⬜ Buttons work
⬜ Internal links work
⬜ External links work
⬜ Phone links work
⬜ WhatsApp link works
⬜ Email link works
⬜ Contact form works
⬜ Form validation works
⬜ Success/error messages work
⬜ Map works
⬜ Social links work
⬜ Gallery works
⬜ Sliders/carousels work
⬜ Any required animations work
11. Responsive Testing
Test at minimum:
Desktop
⬜ 1920px
⬜ 1440px
⬜ 1366px
⬜ 1280px
Tablet
⬜ 1024px
⬜ 768px
Mobile
⬜ 430px
⬜ 414px
⬜ 390px
⬜ 375px
⬜ 320px
Check:
⬜ No horizontal scrolling
⬜ No overlapping elements
⬜ No text clipping
⬜ Buttons fit correctly
⬜ Images scale correctly
⬜ Cards stack correctly
⬜ Navigation works
⬜ Typography remains readable
⬜ Sections maintain correct spacing
12. Visual Accuracy Testing
This should be a separate testing stage, especially when the website is being built from a design.
Compare reference vs website
⬜ Header height
⬜ Logo size
⬜ Navigation position
⬜ Hero height
⬜ Hero image
⬜ Image crop
⬜ Heading position
⬜ Heading size
⬜ Paragraph width
⬜ Button size
⬜ Section spacing
⬜ Container width
⬜ Card dimensions
⬜ Card gaps
⬜ Typography
⬜ Colors
⬜ Borders
⬜ Border radius
⬜ Shadows
⬜ Footer
⬜ Mobile appearance
Visual comparison loop
REFERENCE
↓
IMPLEMENT
↓
SCREENSHOT
↓
COMPARE
↓
IDENTIFY DIFFERENCES
↓
FIX
↓
SCREENSHOT AGAIN
↓
FINAL COMPARISON
⬜ First screenshot captured
⬜ Major differences identified
⬜ Layout corrected
⬜ Typography corrected
⬜ Colors corrected
⬜ Spacing corrected
⬜ Images corrected
⬜ Mobile corrected
⬜ Final screenshot captured
⬜ Client/design approval
13. Browser & Device Testing
Browsers
⬜ Chrome
⬜ Edge
⬜ Firefox
⬜ Safari if applicable
Mobile
⬜ Android browser
⬜ iPhone/Safari if applicable
Check
⬜ Fonts load
⬜ Images load
⬜ Icons load
⬜ Animations work
⬜ Forms work
⬜ Links work
⬜ No console errors
⬜ No failed network requests
14. Performance Testing
⬜ Compress images
⬜ Convert suitable images to WebP/AVIF
⬜ Remove unused assets
⬜ Remove unused dependencies
⬜ Minimize unnecessary JavaScript
⬜ Lazy-load appropriate images
⬜ Check font loading
⬜ Check page load time
⬜ Run Lighthouse
⬜ Check Performance score
⬜ Check Accessibility score
⬜ Check Best Practices
⬜ Check SEO score
15. SEO
Basic SEO
⬜ Page title
⬜ Meta description
⬜ Correct H1
⬜ H2/H3 hierarchy
⬜ Image alt text
⬜ Clean URLs
⬜ Canonical URL if needed
Technical SEO
⬜ robots.txt
⬜ sitemap.xml
⬜ Open Graph metadata
⬜ Social sharing metadata
⬜ Structured data if appropriate
⬜ 404 page
⬜ HTTPS
16. Security
⬜ No API keys inside frontend code
⬜ No passwords in Git
⬜ No private credentials committed
⬜ .env excluded from Git
⬜ Forms protected appropriately
⬜ External services configured securely
⬜ Dependencies checked
⬜ Production configuration reviewed
17. Git & Version Control
⬜ Initial commit
⬜ Commit after major layout
⬜ Commit after functionality
⬜ Commit after testing
⬜ Push to GitHub
⬜ Confirm repository is correct
⬜ Confirm no secrets are committed
⬜ Confirm production build works from clean checkout
Suggested commits:
Initial project setup
Add website structure
Add homepage design
Add responsive layout
Add functionality
Add SEO
Optimize assets
Final QA
Production release
18. Domain Setup
Domain ownership
⬜ Determine domain registrar
⬜ Confirm domain owner
⬜ Confirm login/access
⬜ Confirm domain expiration date
⬜ Confirm renewal status
⬜ Confirm client has ownership/control
DNS
⬜ Identify hosting provider
⬜ Get required DNS records
⬜ Add A record if required
⬜ Add CNAME if required
⬜ Configure www
⬜ Configure root domain
⬜ Remove conflicting records
⬜ Verify DNS propagation
Important
⬜ Do not transfer domain ownership unnecessarily
⬜ Keep client as domain owner
⬜ Record where the domain is registered
⬜ Record renewal date
⬜ Record hosting renewal date
19. Production Build
Before deployment:
⬜ Run production build
⬜ Fix build errors
⬜ Fix warnings where relevant
⬜ Test production build locally
⬜ Verify all assets
⬜ Verify routes
⬜ Verify forms
⬜ Verify environment variables
⬜ Verify API endpoints
⬜ Verify favicon
⬜ Verify metadata
20. Hosting Setup
⬜ Create hosting account
⬜ Connect GitHub repository
⬜ Select production branch
⬜ Configure build command
⬜ Configure output directory
⬜ Configure environment variables
⬜ Deploy
⬜ Check deployment logs
⬜ Fix deployment errors
⬜ Verify production URL
21. Domain → Hosting Connection
⬜ Add custom domain
⬜ Configure DNS
⬜ Verify domain
⬜ Configure www
⬜ Configure root domain
⬜ Enable HTTPS
⬜ Confirm SSL certificate
⬜ Test HTTP → HTTPS redirect
⬜ Test both:
⬜ domain.com
⬜ www.domain.com
22. Final Production Testing
Open the actual production domain, not localhost.
Homepage
⬜ Loads correctly
⬜ Images load
⬜ Fonts load
⬜ Header works
⬜ Navigation works
⬜ Buttons work
⬜ Footer works
Every page
⬜ Page loads
⬜ URL works
⬜ Images work
⬜ Links work
⬜ Forms work
⬜ Mobile layout works
Technical
⬜ HTTPS works
⬜ No mixed-content errors
⬜ No console errors
⬜ No broken links
⬜ No missing assets
⬜ No 404 errors
⬜ No horizontal overflow
23. Final SEO Verification
On production:
⬜ Page title correct
⬜ Meta description correct
⬜ H1 correct
⬜ Images have alt text
⬜ robots.txt works
⬜ Sitemap works
⬜ Canonical URL correct
⬜ Open Graph image works
⬜ Search-engine indexing settings correct
24. Analytics & Tracking
If required:
⬜ Create analytics account
⬜ Add tracking code
⬜ Verify tracking
⬜ Configure important events
⬜ Contact form tracking
⬜ CTA tracking
⬜ WhatsApp click tracking
⬜ Phone click tracking
25. Client Review
Send the production website to the client.
⬜ Client reviewed desktop
⬜ Client reviewed mobile
⬜ Client checked content
⬜ Client checked contact information
⬜ Client checked images
⬜ Client checked links
⬜ Client submitted corrections
⬜ Corrections completed
⬜ Final approval received
26. Final Handover
Website
⬜ Production URL
⬜ GitHub repository
⬜ Hosting account information
⬜ Domain registrar information
⬜ DNS information
⬜ Analytics access
⬜ Form/email service information
Documentation
⬜ Website technology documented
⬜ Deployment process documented
⬜ Domain renewal date documented
⬜ Hosting renewal date documented
⬜ Third-party services documented
⬜ Important credentials handed over securely
Files
⬜ Source code
⬜ Original images
⬜ Logo files
⬜ Design files
⬜ Content files
⬜ Documentation
27. Maintenance Setup
⬜ Determine who maintains website
⬜ Determine maintenance cost
⬜ Determine update process
⬜ Determine backup strategy
⬜ Determine hosting renewal responsibility
⬜ Determine domain renewal responsibility
Monthly/periodic maintenance
⬜ Check website availability
⬜ Check SSL
⬜ Check forms
⬜ Check important links
⬜ Check analytics
⬜ Check hosting
⬜ Check domain expiration
⬜ Update dependencies when appropriate
⬜ Backup website
⬜ Review performance
28. FINAL "DONE" CHECK
The project should not be marked complete until all of these are true:
⬜ Assets collected
⬜ Content approved
⬜ Design approved
⬜ Website built
⬜ All pages completed
⬜ All functionality works
⬜ Responsive design works
⬜ Visual comparison completed
⬜ Browser testing completed
⬜ Performance checked
⬜ SEO completed
⬜ Security checked
⬜ GitHub updated
⬜ Production build works
⬜ Hosting configured
⬜ Domain connected
⬜ HTTPS enabled
⬜ Production website tested
⬜ Client approved
⬜ Handover completed
⬜ Renewal dates recorded
⬜ Maintenance responsibility confirmed
PROJECT STATUS
PROJECT: ______________________________
CLIENT: _______________________________
DOMAIN: _______________________________
HOSTING: ______________________________
START DATE: ___________________________
TARGET DATE: __________________________
CURRENT STAGE:
⬜ Requirements
⬜ Assets
⬜ Content
⬜ Design
⬜ Development
⬜ Testing
⬜ Deployment
⬜ Domain
⬜ Client Review
⬜ Completed
OVERALL STATUS: ______ %
BLOCKERS:
_______________________________________
_______________________________________
NEXT TASK:
_______________________________________
LAST UPDATED:
_______________________________________
Recommended project flow
01 REQUIREMENTS
↓
02 ASSETS
↓
03 CONTENT
↓
04 DESIGN / REFERENCE
↓
05 AI PROMPT
↓
06 PROJECT SETUP
↓
07 BUILD
↓
08 RESPONSIVE
↓
09 FUNCTIONALITY
↓
10 VISUAL QA
↓
11 PERFORMANCE
↓
12 SEO
↓
13 GIT / PRODUCTION BUILD
↓
14 HOSTING
↓
15 DOMAIN + DNS
↓
16 HTTPS
↓
17 PRODUCTION QA
↓
18 CLIENT REVIEW
↓
19 FINAL FIXES
↓
20 HANDOVER
↓
21 MAINTENANCE
↓
DONE
Best practice for your workflow: keep Domain/Hosting until the website is almost finished, but purchase/control the domain early if the client already has one. You can build and test the entire website locally and on a temporary hosting URL first, then connect the real domain only after final QA.