## Checklist
ID | Date | Day | Stage | Task | Priority | Status | Notes
1 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm client/company name | High | done
2 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm website purpose and target audience | High | done
3 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm required pages and sections | High | done
4 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm deadline, scope and approval process | High | done
5 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm domain ownership/registrar | High | done
6 | 15-09-2026 | Tue | Project Setup & Requirements | Confirm hosting requirements | Medium | done
7 | 15-09-2026 | Tue | Assets | Collect official logo | High | done
8 | 15-09-2026 | Tue | Assets | Collect favicon/logo mark | Medium | done
9 | 15-09-2026 | Tue | Assets | Collect brand colors/fonts/guidelines | High | pending | after choosing desinng
10 | 15-09-2026 | Tue | Assets | Collect hero and website images | High | done
11 | 15-09-2026 | Tue | Assets | Collect project/service/team images | High | pending | he will send it
12 | 15-09-2026 | Tue | Assets | Rename, organize and optimize assets | Medium | pending
13 | 15-09-2026 | Tue | Content | Collect all website text/content | High | pending | he will send it
14 | 15-09-2026 | Tue | Content | Verify phone, email, address and social links | High | pending | ask for social links
15 | 15-09-2026 | Tue | Content | Verify legal/footer content | Medium | done
16 | 15-09-2026 | Tue | Content | Get client content approval | High | blocked
17 | 15-09-2026 | Tue | Design | Collect desktop/mobile reference designs | High
18 | 15-09-2026 | Tue | Design | Analyze layout, typography, colors and spacing | High | done
19 | 16-09-2026 | Wed | Design | Analyze responsive behavior | High
20 | 16-09-2026 | Wed | Design | Generate Claude visual-analysis/Copilot prompt | High
21 | 16-09-2026 | Wed | Design | Review and correct AI prompt assumptions | High
22 | 16-09-2026 | Wed | Development | Create/prepare project and Git repository | High
23 | 16-09-2026 | Wed | Development | Set up tech stack and global styles | High
24 | 16-09-2026 | Wed | Development | Build header and navigation | High
25 | 16-09-2026 | Wed | Development | Build hero section | High
26 | 16-09-2026 | Wed | Development | Build remaining homepage sections | High
27 | 16-09-2026 | Wed | Development | Build remaining required pages | High
28 | 16-09-2026 | Wed | Development | Add images/assets and typography | High
29 | 16-09-2026 | Wed | Development | Add buttons, links and interactions | High
30 | 16-09-2026 | Wed | Development | Add contact/WhatsApp/email/map functionality | Medium
31 | 16-09-2026 | Wed | Responsive | Test desktop layout | High
32 | 16-09-2026 | Wed | Responsive | Test tablet layout | High
33 | 16-09-2026 | Wed | Responsive | Test mobile layout | High
34 | 16-09-2026 | Wed | Responsive | Fix overflow, clipping and spacing issues | High
35 | 16-09-2026 | Wed | Testing | Test navigation and all internal links | High
36 | 16-09-2026 | Wed | Testing | Test forms and contact functionality | High
37 | 16-09-2026 | Wed | Testing | Test external/social links | Medium
38 | 16-09-2026 | Wed | Testing | Check browser console for errors | High
39 | 16-09-2026 | Wed | Testing | Check missing/broken images and assets | High
40 | 17-09-2026 | Thu | Visual QA | Capture website screenshots | High
41 | 17-09-2026 | Thu | Visual QA | Compare website against reference design | High
42 | 17-09-2026 | Thu | Visual QA | Fix layout and spacing differences | High
43 | 17-09-2026 | Thu | Visual QA | Fix typography/color differences | High
44 | 17-09-2026 | Thu | Visual QA | Fix image sizing/cropping differences | High
45 | 17-09-2026 | Thu | Visual QA | Final desktop visual comparison | High
46 | 17-09-2026 | Thu | Visual QA | Final mobile visual comparison | High
47 | 17-09-2026 | Thu | Performance & SEO | Optimize images and assets | Medium
48 | 17-09-2026 | Thu | Performance & SEO | Add page titles and meta descriptions | High
49 | 17-09-2026 | Thu | Performance & SEO | Check headings and image alt text | Medium
50 | 17-09-2026 | Thu | Performance & SEO | Run Lighthouse/performance check | Medium
51 | 17-09-2026 | Thu | Production | Run production build | High
52 | 17-09-2026 | Thu | Production | Fix production build errors/warnings | High
53 | 17-09-2026 | Thu | Production | Push final code to GitHub | High
54 | 17-09-2026 | Thu | Hosting | Create/configure hosting | High
55 | 17-09-2026 | Thu | Hosting | Deploy production build | High
56 | 18-09-2026 | Fri | Hosting | Test temporary production URL | High
57 | 18-09-2026 | Fri | Domain | Configure root domain DNS | High
58 | 18-09-2026 | Fri | Domain | Configure www domain DNS | High
59 | 18-09-2026 | Fri | Domain | Enable/verify HTTPS/SSL | High
60 | 18-09-2026 | Fri | Final QA | Test actual production domain | High
61 | 18-09-2026 | Fri | Final QA | Test all pages on production | High
62 | 18-09-2026 | Fri | Final QA | Test mobile on production | High
63 | 18-09-2026 | Fri | Final QA | Check forms, links and contact details on production | High
64 | 18-09-2026 | Fri | Final QA | Check for 404/missing assets/console errors | High
65 | 18-09-2026 | Fri | Client Review | Send final website to client | High
66 | 18-09-2026 | Fri | Client Review | Collect final corrections | High
67 | 18-09-2026 | Fri | Client Review | Complete final corrections | High
68 | 18-09-2026 | Fri | Client Review | Receive final client approval | High
69 | 18-09-2026 | Fri | Handover | Record domain and hosting details | Medium
70 | 18-09-2026 | Fri | Handover | Record renewal dates | Medium
71 | 18-09-2026 | Fri | Handover | Hand over source code/assets/documentation | Medium
72 | 18-09-2026 | Fri | Handover | Confirm maintenance responsibility | Medium

## Deadline Plan
Item | Details
Project Deadline | 18-09-2026 (Friday)
Working Days | 15-09-2026 to 18-09-2026
Day 1 | Requirements + Assets + Content + Design
Day 2 | Project Setup + Main Development
Day 3 | Complete Development + Responsive + Testing + Visual QA
Day 4 | Production + Hosting + Domain + Final QA + Client Approval
Rule | All tasks must be completed or explicitly marked blocked before final handover.